| Approximate Timeline from the Onsite Review | Task | Responsible Party | Completed/Comments |
| --- | --- | --- | --- |
| Pre Onsite QSR |
| 7-6 months prior | County Administrator notified of selection to participate in CQI phase | OCYF Regional Office (RO) Bureau Director or designee |  |
| 7-6 months prior | Identify State and Local Site Leads and any needed case selection/logistics leads | County Administrator or designee (for Local Site Leads) and OCYF RO Bureau Director and Dept. Lead for CWRC OE/Regional Teams and CQI Project Managers (for State Site Leads) |  |
| 6 months prior | Notification Meeting | State Site Leads |  |
| 6 months prior | Contact CQI Project Managers to request technical assistance session | Local and State Site Leads | (If needed/requested) |
| 6 months prior | Selection of dates for trainings (2 day training and Refresher Session), Onsite Review, and Focus Groups | Local and State Site Leads |  |
| 6 months prior | Establish “Effective Sampling Date” (90 days prior to day one of the onsite review) | Local and State Site Leads |  |
| 6-5 months prior | Begin completion of the QSR Team Chart | Local and State Site Leads | (Identify one site lead be lead for editing this chart) |
| 6-3 months prior | Recruit reviewers for Local and State Review Teams | Local and State Site Leads |  |
| 6-3 months prior | Room and equipment reservations for 2 day training, Refresher Session, Onsite QSR and focus groups. | Local Site Leads |  |
| 6-3 months prior | Identify and confirm trainer for 2 day training. | State and Local Site Leads / CWRC Resource Specialist |  |
| 6-3 months prior | Identify and confirm Site Lead trainer for Refresher Session. | State and Local Site Leads / CWRC Resource Specialist |  |
| 6-3 months prior | Determine/develop Power Point and other materials for Orientation Meetings #1 and/or #2. | State and Local Site Leads |  |
| 6-3 months prior | Orientation Meetings #1 and #2 | State and Local Site Leads |  |
| 4-3 months prior | Reviewer selection-Identify and confirm local and state review team members | Local and State Site Leads | (CWRC Resource Specialists can assist in recruitment) |
| 4-3 months prior | Notification of local reviewers to County’s Leadership Team/Administrator | Local Site Leads |  |
| 3 months prior | Prepare In-Home and Out-of-Home case sample lists and submit spreadsheets via secure e-government | Local Site Leads and County AFCARS Contact |  |
| 3 months prior | Randomized case sample lists sent to County AFCARS contact (via secure E-government) and County Site Leads notified that sample has been sent | Hornby Zeller Associates Leads and OCYF CQI Lead |  |
| 3 months up to date of onsite review | Identify eligible cases for the In-Home and Out-of-Home samples and submit working case lists and case exclusion requests to HZA Sampling Leads. | Local and State Site Leads and HZA Sampling Leads |  |
| 3-2 months prior | Send identified reviewers notice of training dates and review dates and collect contact info and details from reviewers | State and Local Site Leads/ CWRC Resource Specialist |  |
| 3-2 months prior | Update QSR Team Chart with Reviewer’s names, contact information, additional info. And preferred week (if applicable) | State and Local Site Leads |  |
| 10-8 weeks prior | Notification of selected cases to the County’s Leadership Team/Administrator | Local Site Leads |  |
| 10-8 weeks prior | Identification of selected cases to Week 1 or Week 2 of review (if applicable) | Local and State Site Leads |  |
| 10-5 weeks prior | Case Summary and Contact Sheets, completed QSR Roll-up sheets (hard copy), and copies of releases of information due to County Site Lead | Caseworkers / Local Site Leads |  |
| 8 weeks prior | State and Local review team members pairing. Update QSR Team Chart with this information. | State and Local Site Leads | Determine eligibility of any QSR reviewers who are eligible for QSR reviewer reimbursement |
| 8 weeks prior | Reserve laptops and cars as needed for QSR onsite week(s). | Local Site Leads |  |
| 8 weeks prior | Identify the type of focus groups to be held (caseworker, supervisor, etc.) along with potential participants. Confirm previously identified focus group dates. | State and Local Site Leads |  |
| 8-6 weeks prior | Invite focus group participants and determine stakeholder interviews | Local Site Leads |  |
| 8-6 weeks prior | Develop purpose statement for focus groups and develop script of questions |  | CWRC evaluation staff available to review purpose statement and script (allow time for consultation and finalization) |
| 8-6 weeks prior | Confirm logistics and equipment for the two day and refresher trainings, onsite review and focus groups. | Local Site Leads |  |
| 8-6 weeks prior | Update QSR Review Week handout to include information on the scheduled focus group dates, times and locations. | State Site Leads |  |
| 8-6 weeks prior | Development of information /Power Point for Orientation Meeting #3. | State and Local Site Leads |  |
| 6 weeks prior | Orientation Meeting #3 | Local Site Leads and State Site Leads (if requested) |  |
| 5 weeks prior | Meet with Caseworkers to discuss and confirm necessary interviews and releases of information | Local Site Leads |  |
| 5 weeks prior | Determine gift cards or food (if applicable) for non-agency focus group participants. | Local Site Leads | Not required |
| 5-4 weeks prior | Prepare and email out training materials for 2 day and Refresher Session trainings | CWRC Resource Specialist/CWRC Administrative Assistant |  |
| 5-4 weeks prior | Hold a conference call with the 2 day trainer to review the county’s specific QSR information | CWRC Trainer, State and Local Site Leads |  |
| 5-2 weeks prior | Schedule interviews and send confirmation letters | Local Site Leads |  |
| 5-2 weeks prior | Plan for any case reviews/interviews that will take 1-2 hours or more of drive time. | Local and State Site Leads |  |
| 5-2 weeks prior | Send training confirmation letters for the 2 day and Refresher Session trainings | CWRC Resource Specialist/CWRC Administrative Staff |  |
| 4 weeks prior | Confirm focus group participants and stakeholder interviews | Local Site Leads |  |
| 4-3 weeks prior | Assign cases to review team pairs | Local and State Site Leads |  |
| 4-1 weeks prior | QSR Reviewer Training | CWRC Trainers; QSR Reviewers; Local and State Site Leads |  |
| 4-1 weeks prior | Confirm transportation needs | Local and State Site Leads |  |
| 3-2 weeks prior | Prepare case files and ensure access for reviewers | Local Site Leads |  |
| 3-2 weeks prior | Send out invitation to Exit Conference | Local Site Leads |  |
| 2-1 weeks prior | Prepare packets for reviewers | Local Site Leads |  |
| 2-1 weeks prior | Secure flash drives from HZA | Local and State Site Leads |  |
| 1 week prior | Finalize interview schedules (expect last minute changes) | Local Site Leads |  |
| 1 week prior | Proof interview schedules | State Site Leads |  |
| 1 week prior | Send completed interview schedules to assigned caseworker and supervisor | Local Site Leads | Materials are to be password protected |
| 1 week prior | Send completed interview schedules and case summaries to assigned reviewers. | State and Local Site Leads |  |
| 1 week prior | Prepare QSR Participant surveys for distribution during the onsite review week | Local Site Leads |  |
| 1 week prior | Finalize QSR Team Chart and contact information | State and Local Site Leads | Submit to CQI Project Manager, Statewide Resource Specialist and HZA Representative |
| 2-1 days prior | Set up on-site review rooms with packets and supplies | Local Site Leads |  |
| Onsite QSR |
| Onsite QSR | Provide onsite technical assistance to Review Teams | State and Local Site Leads |  |
| Onsite QSR (unless determined differently) | Conduct Focus Groups | State Site Leads and/or outside facilitator |  |
| Onsite QSR | Facilitate the Case-Specific Team Debriefings and conduct 2nd level QA | State and Local Site Leads |  |
| Onsite QSR | Collect and validate QSR Roll-Up Sheets and email to HZA | State and Local Site Leads/HZA Assistance |  |
| Onsite QSR | Develop Exit Conference Agenda, Power Point and additional handouts. | State and Local Site Leads |  |
| Onsite QSR | Facilitate Exit Conference of preliminary findings | State and Local Site Leads |  |
| Onsite QSR | Collect all flash drives. | State and Local Site Leads |  |
| Onsite QSR | Disseminate the QSR Participant and QSR Reviewer Feedback Forms | State and Local Site Leads | If requested, links to web-based Feedback Forms can be sent to QSR Reviewers and QSR Participants, but Local and State Site Leads will need to provided email addresses of recipients to CQI Project Lead |
| Post Onsite QSR – Final Report and QSR Result Highlights Report |
| 1-3 weeks following the onsite QSR | Conduct second level QA of QSR Roll-Up sheets; Alert HZA Lead and CQI Project Manager that Roll-Up Sheets have been finalized | State and Local Site Leads |  |
| 1-3 weeks following the onsite QSR | Return flash drives to HZA | State and Local Site Leads |  |
| 1-3 weeks following the onsite QSR | Share the finalized QSR Roll-Up Sheet Report with the caseworkers and supervisors whose cases were reviewed | Local Site Leads |  |
| 1-3 weeks following the onsite QSR (if focus groups occurred during the onsite QSR) | Focus Group Facilitator and Note Taker conduct review of focus group information and submit purpose statement, script of questions and notes to HZA Lead | Focus Group Facilitators and Note Takers | If focus group(s) is/are not conducted during onsite QSR, then focus group purpose statement(s), script(s) of questions, and notes are to be submitted to HZA Lead and CQI Project Mangers |
| 3 weeks following the onsite QSR | Collect feedback survey data from interviewees and reviewers (if not previously submitted) | State and Local Site Leads |  |
| 1-2 weeks after securing the QSR Final Report | Share the QSR Final Report with the County Administrator | State and Local Site Leads |  |
| 3 weeks after receiving the QSR Final Report from HZA | Review QSR Final Report. Submit priority areas requested for further analysis to HZA so they can develop the QSR Result Highlights, if requested by the County. | State and Local Site Leads in collaboration with the County Administrator and/or leadership of the County |  |
| Approximately 2 weeks after receiving the County’s priority areas for further analysis | Send QSR Result Highlights, which includes analysis of priority areas sent to Local and State Site Leads. | Hornby Zeller Associates |  |
| Post Onsite QSR – Next Steps Meeting |
| 4 weeks prior to the Next Steps Meeting | Send out invitation including time and location for the Next Steps Meeting | Local Site Leads |  |
| 2 weeks prior to the Next Steps Meeting | Develop agenda, Power Point and additional handouts for the Next Steps Meeting | State and Local Site Leads |  |
| 10 -12 weeks after the Onsite QSR | Next Steps Meeting | State and Local Site Leads |  |
| Post Onsite QSR – County Improvement Plan |
| 120 days following the last day of the onsite QSR | Submit County Improvement Plan (CIP) to OCYF Regional Office Director with cc: to Local and State Site Lead Team and CQI Project Managers | Local Site Leads | TA Collaborative members including CWRC staff and OCYF RO staff are available to assist with CIP development |
| 10 business days from receipt of CIP | Acceptance of County Improvement Plan to County Administrator and cc: Local and State Site Leads and CQI Project Managers | OCYF Regional Office Director |  |